## Plan
Plan ID | Plan name | Date of export
TYiVlmBUQUemx5oHaPW3OsgAEjRb | 49-teamA-A1_T3_plan | 2026-08-16

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
Yi-Y5wpfAUmz9gtXPTr69cgAKAl6 | Project Bootstrap & Repository Setup : Week 1 - 4 hours | Infrastructure |  | Not started | Medium | Thomas Williams | Sherlene Andrew | 2026-08-16 |  |  |  | false |  |  |  |  | DEV;Sprint 1
uutjtCByZku7Hu7_5hgeXsgANBCy | Technical Responsibilities & Dependencies : Week 1 - 4 hours | Infrastructure |  | Not started | Medium | Wangfung Chu | Sherlene Andrew | 2026-08-16 |  |  |  | false |  |  |  |  | DEV;Sprint 1
RWqKXKh5tUqxtOW1KDeBMsgAAChj | Technical Architecture & Sync Planning : Week 2 - 4 hours | Infrastructure |  | Not started | Medium | Wangfung Chu | Sherlene Andrew | 2026-08-16 |  |  |  | false |  |  |  |  | DEV;Sprint 1
_cvaPM9GWUmSnuvJTKlevcgANlFj | Development Environment Verification : Week 2 - 4 hours | Infrastructure |  | Not started | Medium | Thomas Williams | Sherlene Andrew | 2026-08-16 |  |  |  | false |  |  |  |  | DEV;Sprint 1
yBWEzr5LqE6FGlfNiyPO28gACjRn | Finalise Technical Planning : Week 3 - 4 hours | Infrastructure |  | Not started | Medium | Wangfung Chu | Sherlene Andrew | 2026-08-16 |  |  |  | false |  |  |  |  | DEV;Sprint 1
QqaJ0vHa1EmDv6sJ8dIsLsgAErBx | Final Bootstrap Verification : Week 3 - 4 hours | Infrastructure |  | Not started | Medium | Thomas Williams | Sherlene Andrew | 2026-08-16 |  |  |  | false |  |  |  |  | DEV;Sprint 1
tpc879chTE28DEyFVqFjm8gAP2dO | Initial Requirements & Business Rules : Week 1 - 4 hours | Design / Product |  | Not started | Medium | Devlyn Jay | Sherlene Andrew | 2026-08-16 |  |  |  | false |  |  |  |  | Sprint 1;BA
nZtRXrj2h0qvbNLBZwXr_MgAEKX_ | Initial Dashboard UX Direction : Week 1 - 4 hours | Design / Product |  | Not started | Medium | Jonas Inocencio | Sherlene Andrew | 2026-08-16 |  |  |  | false |  |  |  |  | Sprint 1;UX/DEV
AnEeFMq03EWX-KcrfN76icgAA_81 | Sprint Planning & Risk/Dependency Tracking : Week 1 - 4 hours | Design / Product |  | Not started | Medium | Sherlene Andrew | Sherlene Andrew | 2026-08-16 |  |  |  | false |  |  |  |  | PM;Sprint 1
aoDUqFSYOUyhw_vdD-lLrsgAPSoa | Requirements Review & Scope Validation : Week 2 - 4 hours | Design / Product |  | Not started | Medium | Devlyn Jay | Sherlene Andrew | 2026-08-16 |  |  |  | false |  |  |  |  | Sprint 1;BA
jFVQWKhvIEKfTLuhJP0jRcgANbLg | Dashboard UX Refinement : Week 2 - 4 hours | Design / Product |  | Not started | Medium | Jonas Inocencio | Sherlene Andrew | 2026-08-16 |  |  |  | false |  |  |  |  | Sprint 1;UX/DEV
xfornmOQckOBIj-Uhng-EMgANOsq | Sprint Progress & Dependency Review : Week 2 - 4 hours | Design / Product |  | Not started | Medium | Sherlene Andrew | Sherlene Andrew | 2026-08-16 |  |  |  | false |  |  |  |  | PM;Sprint 1
D7Mn2MMU-kWt2fL9EfWPK8gAMhdQ | Finalise Requirements & Acceptance Criteria : Week 3 - 4 hours | Design / Product |  | Not started | Medium | Devlyn Jay | Sherlene Andrew | 2026-08-16 |  |  |  | false |  |  |  |  | Sprint 1;BA
BCih29llv0SgjRt8OaNo1cgADXJm | Finalise Dashboard UX Prototype : Week 3 - 4 hours | Design / Product |  | Not started | Medium | Jonas Inocencio | Sherlene Andrew | 2026-08-16 |  |  |  | false |  |  |  |  | Sprint 1;UX/DEV
BOZx9amElUSOuyo-Yr-XbcgANkmG | Sprint 1 Review & Sign-Off : Week 3 - 4 hours | Design / Product |  | Not started | Medium | Sherlene Andrew | Sherlene Andrew | 2026-08-16 |  |  |  | false |  |  |  |  | PM;Sprint 1

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
Yi-Y5wpfAUmz9gtXPTr69cgAKAl6 | Project Bootstrap & Repository Setup : Week 1 - 4 hours | tGmXHe6qVEivfgcl6bJbm8gALhA8 |  | Not started | Medium | fbf7c6e5-5096-4832-be13-ae3a8b7e3f66 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-16 |  |  |  | false |  |  |  |  | DEV;Sprint 1
uutjtCByZku7Hu7_5hgeXsgANBCy | Technical Responsibilities & Dependencies : Week 1 - 4 hours | tGmXHe6qVEivfgcl6bJbm8gALhA8 |  | Not started | Medium | a707c21a-ae80-4a96-9809-71b38104eefb | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-16 |  |  |  | false |  |  |  |  | DEV;Sprint 1
RWqKXKh5tUqxtOW1KDeBMsgAAChj | Technical Architecture & Sync Planning : Week 2 - 4 hours | tGmXHe6qVEivfgcl6bJbm8gALhA8 |  | Not started | Medium | a707c21a-ae80-4a96-9809-71b38104eefb | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-16 |  |  |  | false |  |  |  |  | DEV;Sprint 1
_cvaPM9GWUmSnuvJTKlevcgANlFj | Development Environment Verification : Week 2 - 4 hours | tGmXHe6qVEivfgcl6bJbm8gALhA8 |  | Not started | Medium | fbf7c6e5-5096-4832-be13-ae3a8b7e3f66 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-16 |  |  |  | false |  |  |  |  | DEV;Sprint 1
yBWEzr5LqE6FGlfNiyPO28gACjRn | Finalise Technical Planning : Week 3 - 4 hours | tGmXHe6qVEivfgcl6bJbm8gALhA8 |  | Not started | Medium | a707c21a-ae80-4a96-9809-71b38104eefb | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-16 |  |  |  | false |  |  |  |  | DEV;Sprint 1
QqaJ0vHa1EmDv6sJ8dIsLsgAErBx | Final Bootstrap Verification : Week 3 - 4 hours | tGmXHe6qVEivfgcl6bJbm8gALhA8 |  | Not started | Medium | fbf7c6e5-5096-4832-be13-ae3a8b7e3f66 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-16 |  |  |  | false |  |  |  |  | DEV;Sprint 1
tpc879chTE28DEyFVqFjm8gAP2dO | Initial Requirements & Business Rules : Week 1 - 4 hours | oK6qTdv6JUm5uAr5cABiJMgALhQ_ |  | Not started | Medium | e34c9a79-4046-4931-9ad4-841f69cc8471 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-16 |  |  |  | false |  |  |  |  | Sprint 1;BA
nZtRXrj2h0qvbNLBZwXr_MgAEKX_ | Initial Dashboard UX Direction : Week 1 - 4 hours | oK6qTdv6JUm5uAr5cABiJMgALhQ_ |  | Not started | Medium | e94ba878-f30a-4cb6-8d83-0fa53451575c | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-16 |  |  |  | false |  |  |  |  | Sprint 1;UX/DEV
AnEeFMq03EWX-KcrfN76icgAA_81 | Sprint Planning & Risk/Dependency Tracking : Week 1 - 4 hours | oK6qTdv6JUm5uAr5cABiJMgALhQ_ |  | Not started | Medium | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-16 |  |  |  | false |  |  |  |  | PM;Sprint 1
aoDUqFSYOUyhw_vdD-lLrsgAPSoa | Requirements Review & Scope Validation : Week 2 - 4 hours | oK6qTdv6JUm5uAr5cABiJMgALhQ_ |  | Not started | Medium | e34c9a79-4046-4931-9ad4-841f69cc8471 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-16 |  |  |  | false |  |  |  |  | Sprint 1;BA
jFVQWKhvIEKfTLuhJP0jRcgANbLg | Dashboard UX Refinement : Week 2 - 4 hours | oK6qTdv6JUm5uAr5cABiJMgALhQ_ |  | Not started | Medium | e94ba878-f30a-4cb6-8d83-0fa53451575c | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-16 |  |  |  | false |  |  |  |  | Sprint 1;UX/DEV
xfornmOQckOBIj-Uhng-EMgANOsq | Sprint Progress & Dependency Review : Week 2 - 4 hours | oK6qTdv6JUm5uAr5cABiJMgALhQ_ |  | Not started | Medium | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-16 |  |  |  | false |  |  |  |  | PM;Sprint 1
D7Mn2MMU-kWt2fL9EfWPK8gAMhdQ | Finalise Requirements & Acceptance Criteria : Week 3 - 4 hours | oK6qTdv6JUm5uAr5cABiJMgALhQ_ |  | Not started | Medium | e34c9a79-4046-4931-9ad4-841f69cc8471 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-16 |  |  |  | false |  |  |  |  | Sprint 1;BA
BCih29llv0SgjRt8OaNo1cgADXJm | Finalise Dashboard UX Prototype : Week 3 - 4 hours | oK6qTdv6JUm5uAr5cABiJMgALhQ_ |  | Not started | Medium | e94ba878-f30a-4cb6-8d83-0fa53451575c | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-16 |  |  |  | false |  |  |  |  | Sprint 1;UX/DEV
BOZx9amElUSOuyo-Yr-XbcgANkmG | Sprint 1 Review & Sign-Off : Week 3 - 4 hours | oK6qTdv6JUm5uAr5cABiJMgALhQ_ |  | Not started | Medium | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-16 |  |  |  | false |  |  |  |  | PM;Sprint 1

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
tGmXHe6qVEivfgcl6bJbm8gALhA8 | Infrastructure
oK6qTdv6JUm5uAr5cABiJMgALhQ_ | Design / Product

## Users
User ID | User Name | Email
fbf7c6e5-5096-4832-be13-ae3a8b7e3f66 | Thomas Williams | s4005637@student.rmit.edu.au
ff7648f0-ec7a-4459-a9b2-dda9413432c9 | Sherlene Andrew | s4003502@student.rmit.edu.au
a707c21a-ae80-4a96-9809-71b38104eefb | Wangfung Chu | S3942078@student.rmit.edu.au
e34c9a79-4046-4931-9ad4-841f69cc8471 | Devlyn Jay | S3844511@student.rmit.edu.au
e94ba878-f30a-4cb6-8d83-0fa53451575c | Jonas Inocencio | S3787701@student.rmit.edu.au