## Plan
Plan ID | Plan name | Date of export
ZgBmdeRPlEa1nYqU8Zxjz8gAFj-3 | Week 4 - project: Team 49 | 2026-08-16

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
37-P9KQhpU-6akcY_cS1IsgAHr-R | Labels | Documents & Updates |  | Not started | Medium |  | Sherlene Andrew | 2026-08-15 |  |  |  | false
R3SENN-O8EiWDq9LJ7NHZsgAHO03 | [BOOTSTRAP RESTYLING] -Write requirements for team page + login styling : 60 | Done |  | Completed | Important | Devlyn Jay | Sherlene Andrew | 2026-08-15 |  |  |  | false | 2026-08-16 | Sherlene Andrew | 5/5 | Edge cases documented;Requirements shared with PM and UX;Document updated;Login scope explicitly stated as styling-only;Team page fields listed with validation/display rules | BA;Sprint 1 | Description Determine the content fields for the team page (name, photo, role, blurb) and confirm the login work is styling only, with no changes to existing auth logic or session behavior. Document edge cases such as missing photos or long blurb text. Update Everything on Master-Document-EXAMPLE.docx
TpmWWaUbEUCfYjlH_AaYIcgAGhFZ | [BOOTSTRAP RESTYLING] Design Login Style & Team Page Layout :120 | Done |  | Completed | Medium | Jonas Inocencio | Sherlene Andrew | 2026-08-15 |  |  |  | false | 2026-08-15 | Jonas Inocencio | 5/5 | Login page mockup complete;Team page mockup complete;Document Updated;Design shared with BA for validation;Visual consistency between the two checked | UX;Sprint 1 | Produce a mockup/wireframe of the restyled login page and a separate mockup of the team page layout, based on the BA's requirements document. Both must be visually consistent with each other. Completion comment Done: Created mockups for restyled login and register page, as well as the team page. Each page uses similar design language to ensure web design consistency. Placeholder team headshots have been used, as has placeholder lorem ipsum for blurbs. Long-blurb cases have been handled with a scroll bar. Deliverable: Figma file, linked from the team repo; PDF export of each individual page; SVG placeholder image for team member photograph. https://github.com/ThomasRMIT/team-49-mock-sprint/tree/dependabot/github_actions/actions/checkout-7/docs/design Note for next role: BA — Blurbs that are too long show a scroll bar. Please ensure this is acceptable prior to approval.
FA6wvbZ-GU-4cqlRagC9dsgAEDJd | [BOOTSTRAP RESTYLING]- Validate Design Against Requirements : 60 | Done |  | Completed | Medium | Devlyn Jay | Sherlene Andrew | 2026-08-15 |  |  |  | false | 2026-08-16 | Sherlene Andrew | 5/5 | Login scope confirmed unchanged;Design formally approved;Every required field checked against the design;Document Updated;Gaps (if any) sent back to UX and resolved | BA;Sprint 1 | Check the UX mockups against the requirements document. Confirm every field is represented, the login mockup stays styling-only, and edge cases have a visible design treatment. Flag any gaps back to UX before approving. Update Master-Document-EXAMPLE.docx
UDkxI6kKCUuGM0FVFYp_kcgADMzv | [BOOTSTRAP RESTYLING]- Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only : 60 | Done |  | Completed | Medium | Thomas Williams | Sherlene Andrew | 2026-08-15 |  |  |  | false | 2026-08-15 | Thomas Williams | 4/4 | Existing login validation/errors still function as before;Update document;Visual style matches approved mockup;No authentication logic changed | DEV;Sprint 1 | Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only. Master-Document-EXAMPLE.docx Completion notes: Done: Implemented the approved login and signup page styling. Confirmed with team that logic and code functionality remains untouched Deliverable: Branch/commit with the styling changes. Note for next role: Nothing blocking — moving straight on to the team page build myself.
WZENLYufFk2NtXRNLd1GxcgACZMq | [BOOTSTRAP RESTYLING]- Build Team Page & Auth Redirect : 120 | Done |  | Completed | Medium | Thomas Williams | Sherlene Andrew | 2026-08-15 |  |  |  | false | 2026-08-15 | Thomas Williams | 4/4 | Document updated;Successful login redirects to team page;Team page not directly accessible without login;Team page renders per design with all required fields | DEV;Sprint 1 | Build the team page per the approved design (name, member cards, blurb) and wire it so a successful login redirects the user here. The team page itself should not be reachable without a valid login. Done: Team page built following the design structure including blurb, login now redirects to team page and team page redirects to login if accessed without authentication Deliverable: Branch/commit with the team page and route guard. Note for next role: Dev 2 — please test against the deployed URL once it's live, not localhost.
0GUqb8NUpUKIQwNCoKbkEMgAJk_0 | [BOOTSTRAP RESTYLING] - Deploy - 120 | Done |  | Completed | Medium | Thomas Williams | Sherlene Andrew | 2026-08-15 |  |  |  | false | 2026-08-15 | Thomas Williams | 4/4 | Deployment completed via boilerplate pipeline;Login → redirect → team page flow spot-checked on the deployed URL;Live URL loads without errors;Document updated | DEV;Sprint 1 | Deploy the updated application (restyled login + team page + redirect) using the boilerplate's deployment pipeline. Confirm the deployed version is live and functioning before handing off to Dev 2. Update Doc Master-Document-EXAMPLE.docx Completion notes: Site has been deployed and confirmed live and functioning https://team-49-mock-sprint-frontend.vercel.app/
7nrLibQW3UuWVdFyrRY1pMgAFeM7 | [BOOTSTRAP RESTYLING] Test Login → Redirect → Team Page Flow : 60 | Done |  | Completed | Medium | Wangfung Chu | Sherlene Andrew | 2026-08-15 |  | 2026-08-15 |  | false | 2026-08-16 | Sherlene Andrew | 4/4 | Valid login tested end-to-end on deployed URL;All required content verified correct and complete;Redirect to team page confirmed;Document updated | DEV;Sprint 1 | On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Update Document Master-Document-EXAMPLE.docx
O9n8F0UszkyqP79R8t2XXsgABx4D | [BOOTSTRAP RESTYLING] - Test Edge Cases & Log Bugs : 60 | Done |  | Completed | Medium | Wangfung Chu | Sherlene Andrew | 2026-08-15 |  | 2026-08-15 |  | false | 2026-08-16 | Sherlene Andrew | 5/5 | Direct team-page access without login tested (must redirect);Missing-photo and long-blurb edge cases tested;Bugs logged with repro steps, or none-found confirmed;Update Document;Invalid login tested | DEV;Sprint 1 | Test edge cases identified by the BA: invalid login, direct team-page access without logging in, a missing photo, and an unusually long blurb. Log any bugs found back to Dev 1 with reproduction steps. Update DocMaster-Document-EXAMPLE.docx
qaV9ikx2t0yQRIzKX9mPTcgADOpv | [BOOTSTRAP RESTYLING] - Final Review & Sign-Off : 30 | Done |  | Completed | Medium | Sherlene Andrew | Sherlene Andrew | 2026-08-15 |  |  |  | false | 2026-08-16 | Sherlene Andrew | 3/3 | All prior tasks' checklists verified complete;Task moved to Done;Feature reviewed end-to-end against requirements and design | PM;Sprint 1 | PM reviews the completed feature end-to-end against the original requirements and design, confirms every prior task's checklist is complete, and signs off. Update Master-Document-EXAMPLE.docx Document is finalized and signed off
ZfroUXUYLEeQw0EJGeSg5sgADD_W | Instructions | Documents & Updates |  | Not started | Medium |  | Sherlene Andrew | 2026-08-15 |  |  |  | false | [5 empty] | Assign your roles Before touching anything, agree as a team who is PM, BA, UX, Dev 1, and Dev 2. Assign each task on the board to the real person doing it. If your team has fewer than five people, roles can combine. PM Creates the tasks After discussing with the reast of the team, the PM Creates the high level tasks with the description and agrees with the rest of the team on the requirements and the time it requires. You can use many techniques to estimate how long the tasks will take, assume junior level experience. For example creating a set of API end points will take 30 minutes, but a person with no knowledge may require 2 hours. This task still only counts for 30 minutes. Every student can spend up to 10 hours on the project, if a student does not know how to complete the task, this will require them to spend their own remaining time (this means that the real budget is 10 hours not 4). Planning poker can be a good way to make an estimate. (7) Planning Poker Estimation in Scrum: A Guide to Accurate Time Estimation ¦ LinkedIn Update every task as you go Move the card into your column only when you're actually starting it. Don't work ahead. Tick off each item in the Acceptance Criteria checklist as you genuinely complete it — not before. Add a completion comment before moving the card forward: what you did, where the deliverable lives, and anything the next person needs to know. Do this in the card's Notes field — chat/tagging is fine for ongoing discussion, but the handoff itself must be left in the notes. Move the card into the next bucket immediately once it's done. The board should always reflect reality, not what you'll update "later." Handoff structure Once completed make sure to add a note in the notes with your handoff Done: one line on what you actually completed. Deliverable: a link to where it lives (doc, design file, branch/commit, deployed URL). Note for next role: anything the next person needs to know before they start — assumptions you made, edge cases you handled, things you left out of scope. Follow the hard rules — no exceptions No task starts until it's in your column, or it has been assigned to you. Every completion gets a comment before the card moves. Developers never test their own code — Dev 1 builds, Dev 2 tests. The PM writes the cards and signs off last; nobody else marks a task Done.
xzeY5BDyi0aZMlAa6wxHisgAMCkU | [Group 49 1st meeting] : 30 | Documents & Updates |  | Completed | Medium | Wangfung Chu;Thomas Williams;Sherlene Andrew;Jonas Inocencio;Devlyn Jay | Sherlene Andrew | 2026-08-15 | 2026-08-06 | 2026-08-06 |  | false | 2026-08-15 | Sherlene Andrew | 3/3 | Sub Task 2;Sub Task 3;Sub Task 1 | 1st meeting completed | Description (Added by pm) On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Update Document Master-Document-EXAMPLE.docx Completion comment Done: Documented required fields for the team page (team name, project name, per-member photo/name/role, about-us blurb) and confirmed login work is styling-only, no auth logic changes. Deliverable: Requirements document, committed to the team repo. Note for next role: UX — we have 5 team members, one doesn't have a headshot yet, so the design needs a placeholder-avatar treatment. Two members also have longer blurbs, so don't assume a one-line blurb. Git URL: https://github.com/team-byte-size/team-page/blob/main/docs/requirements.md
6a7tE15QBkWzIcnQaYdaUcgAG1q- | Management Notes | Documents & Updates |  | Not started | Medium |  | Alessio Bonti | 2026-08-15 |  |  |  | false | [5 empty] | Not much done and work started without moving things into doing

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
37-P9KQhpU-6akcY_cS1IsgAHr-R | Labels | V87MYN_Sy0qJgvKIHm2EVMgAEggU |  | Not started | Medium |  | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-15 |  |  |  | false
R3SENN-O8EiWDq9LJ7NHZsgAHO03 | [BOOTSTRAP RESTYLING] -Write requirements for team page + login styling : 60 | IyEBllnWwUC7l9NEEtdTxcgACfbp |  | Completed | Important | e34c9a79-4046-4931-9ad4-841f69cc8471 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-15 |  |  |  | false | 2026-08-16 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 5/5 | Edge cases documented;Requirements shared with PM and UX;Document updated;Login scope explicitly stated as styling-only;Team page fields listed with validation/display rules | BA;Sprint 1 | Description Determine the content fields for the team page (name, photo, role, blurb) and confirm the login work is styling only, with no changes to existing auth logic or session behavior. Document edge cases such as missing photos or long blurb text. Update Everything on Master-Document-EXAMPLE.docx
TpmWWaUbEUCfYjlH_AaYIcgAGhFZ | [BOOTSTRAP RESTYLING] Design Login Style & Team Page Layout :120 | IyEBllnWwUC7l9NEEtdTxcgACfbp |  | Completed | Medium | e94ba878-f30a-4cb6-8d83-0fa53451575c | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-15 |  |  |  | false | 2026-08-15 | e94ba878-f30a-4cb6-8d83-0fa53451575c | 5/5 | Login page mockup complete;Team page mockup complete;Document Updated;Design shared with BA for validation;Visual consistency between the two checked | UX;Sprint 1 | Produce a mockup/wireframe of the restyled login page and a separate mockup of the team page layout, based on the BA's requirements document. Both must be visually consistent with each other. Completion comment Done: Created mockups for restyled login and register page, as well as the team page. Each page uses similar design language to ensure web design consistency. Placeholder team headshots have been used, as has placeholder lorem ipsum for blurbs. Long-blurb cases have been handled with a scroll bar. Deliverable: Figma file, linked from the team repo; PDF export of each individual page; SVG placeholder image for team member photograph. https://github.com/ThomasRMIT/team-49-mock-sprint/tree/dependabot/github_actions/actions/checkout-7/docs/design Note for next role: BA — Blurbs that are too long show a scroll bar. Please ensure this is acceptable prior to approval.
FA6wvbZ-GU-4cqlRagC9dsgAEDJd | [BOOTSTRAP RESTYLING]- Validate Design Against Requirements : 60 | IyEBllnWwUC7l9NEEtdTxcgACfbp |  | Completed | Medium | e34c9a79-4046-4931-9ad4-841f69cc8471 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-15 |  |  |  | false | 2026-08-16 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 5/5 | Login scope confirmed unchanged;Design formally approved;Every required field checked against the design;Document Updated;Gaps (if any) sent back to UX and resolved | BA;Sprint 1 | Check the UX mockups against the requirements document. Confirm every field is represented, the login mockup stays styling-only, and edge cases have a visible design treatment. Flag any gaps back to UX before approving. Update Master-Document-EXAMPLE.docx
UDkxI6kKCUuGM0FVFYp_kcgADMzv | [BOOTSTRAP RESTYLING]- Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only : 60 | IyEBllnWwUC7l9NEEtdTxcgACfbp |  | Completed | Medium | fbf7c6e5-5096-4832-be13-ae3a8b7e3f66 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-15 |  |  |  | false | 2026-08-15 | fbf7c6e5-5096-4832-be13-ae3a8b7e3f66 | 4/4 | Existing login validation/errors still function as before;Update document;Visual style matches approved mockup;No authentication logic changed | DEV;Sprint 1 | Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only. Master-Document-EXAMPLE.docx Completion notes: Done: Implemented the approved login and signup page styling. Confirmed with team that logic and code functionality remains untouched Deliverable: Branch/commit with the styling changes. Note for next role: Nothing blocking — moving straight on to the team page build myself.
WZENLYufFk2NtXRNLd1GxcgACZMq | [BOOTSTRAP RESTYLING]- Build Team Page & Auth Redirect : 120 | IyEBllnWwUC7l9NEEtdTxcgACfbp |  | Completed | Medium | fbf7c6e5-5096-4832-be13-ae3a8b7e3f66 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-15 |  |  |  | false | 2026-08-15 | fbf7c6e5-5096-4832-be13-ae3a8b7e3f66 | 4/4 | Document updated;Successful login redirects to team page;Team page not directly accessible without login;Team page renders per design with all required fields | DEV;Sprint 1 | Build the team page per the approved design (name, member cards, blurb) and wire it so a successful login redirects the user here. The team page itself should not be reachable without a valid login. Done: Team page built following the design structure including blurb, login now redirects to team page and team page redirects to login if accessed without authentication Deliverable: Branch/commit with the team page and route guard. Note for next role: Dev 2 — please test against the deployed URL once it's live, not localhost.
0GUqb8NUpUKIQwNCoKbkEMgAJk_0 | [BOOTSTRAP RESTYLING] - Deploy - 120 | IyEBllnWwUC7l9NEEtdTxcgACfbp |  | Completed | Medium | fbf7c6e5-5096-4832-be13-ae3a8b7e3f66 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-15 |  |  |  | false | 2026-08-15 | fbf7c6e5-5096-4832-be13-ae3a8b7e3f66 | 4/4 | Deployment completed via boilerplate pipeline;Login → redirect → team page flow spot-checked on the deployed URL;Live URL loads without errors;Document updated | DEV;Sprint 1 | Deploy the updated application (restyled login + team page + redirect) using the boilerplate's deployment pipeline. Confirm the deployed version is live and functioning before handing off to Dev 2. Update Doc Master-Document-EXAMPLE.docx Completion notes: Site has been deployed and confirmed live and functioning https://team-49-mock-sprint-frontend.vercel.app/
7nrLibQW3UuWVdFyrRY1pMgAFeM7 | [BOOTSTRAP RESTYLING] Test Login → Redirect → Team Page Flow : 60 | IyEBllnWwUC7l9NEEtdTxcgACfbp |  | Completed | Medium | a707c21a-ae80-4a96-9809-71b38104eefb | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-15 |  | 2026-08-15 |  | false | 2026-08-16 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 4/4 | Valid login tested end-to-end on deployed URL;All required content verified correct and complete;Redirect to team page confirmed;Document updated | DEV;Sprint 1 | On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Update Document Master-Document-EXAMPLE.docx
O9n8F0UszkyqP79R8t2XXsgABx4D | [BOOTSTRAP RESTYLING] - Test Edge Cases & Log Bugs : 60 | IyEBllnWwUC7l9NEEtdTxcgACfbp |  | Completed | Medium | a707c21a-ae80-4a96-9809-71b38104eefb | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-15 |  | 2026-08-15 |  | false | 2026-08-16 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 5/5 | Direct team-page access without login tested (must redirect);Missing-photo and long-blurb edge cases tested;Bugs logged with repro steps, or none-found confirmed;Update Document;Invalid login tested | DEV;Sprint 1 | Test edge cases identified by the BA: invalid login, direct team-page access without logging in, a missing photo, and an unusually long blurb. Log any bugs found back to Dev 1 with reproduction steps. Update DocMaster-Document-EXAMPLE.docx
qaV9ikx2t0yQRIzKX9mPTcgADOpv | [BOOTSTRAP RESTYLING] - Final Review & Sign-Off : 30 | IyEBllnWwUC7l9NEEtdTxcgACfbp |  | Completed | Medium | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-15 |  |  |  | false | 2026-08-16 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 3/3 | All prior tasks' checklists verified complete;Task moved to Done;Feature reviewed end-to-end against requirements and design | PM;Sprint 1 | PM reviews the completed feature end-to-end against the original requirements and design, confirms every prior task's checklist is complete, and signs off. Update Master-Document-EXAMPLE.docx Document is finalized and signed off
ZfroUXUYLEeQw0EJGeSg5sgADD_W | Instructions | V87MYN_Sy0qJgvKIHm2EVMgAEggU |  | Not started | Medium |  | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-15 |  |  |  | false | [5 empty] | Assign your roles Before touching anything, agree as a team who is PM, BA, UX, Dev 1, and Dev 2. Assign each task on the board to the real person doing it. If your team has fewer than five people, roles can combine. PM Creates the tasks After discussing with the reast of the team, the PM Creates the high level tasks with the description and agrees with the rest of the team on the requirements and the time it requires. You can use many techniques to estimate how long the tasks will take, assume junior level experience. For example creating a set of API end points will take 30 minutes, but a person with no knowledge may require 2 hours. This task still only counts for 30 minutes. Every student can spend up to 10 hours on the project, if a student does not know how to complete the task, this will require them to spend their own remaining time (this means that the real budget is 10 hours not 4). Planning poker can be a good way to make an estimate. (7) Planning Poker Estimation in Scrum: A Guide to Accurate Time Estimation ¦ LinkedIn Update every task as you go Move the card into your column only when you're actually starting it. Don't work ahead. Tick off each item in the Acceptance Criteria checklist as you genuinely complete it — not before. Add a completion comment before moving the card forward: what you did, where the deliverable lives, and anything the next person needs to know. Do this in the card's Notes field — chat/tagging is fine for ongoing discussion, but the handoff itself must be left in the notes. Move the card into the next bucket immediately once it's done. The board should always reflect reality, not what you'll update "later." Handoff structure Once completed make sure to add a note in the notes with your handoff Done: one line on what you actually completed. Deliverable: a link to where it lives (doc, design file, branch/commit, deployed URL). Note for next role: anything the next person needs to know before they start — assumptions you made, edge cases you handled, things you left out of scope. Follow the hard rules — no exceptions No task starts until it's in your column, or it has been assigned to you. Every completion gets a comment before the card moves. Developers never test their own code — Dev 1 builds, Dev 2 tests. The PM writes the cards and signs off last; nobody else marks a task Done.
xzeY5BDyi0aZMlAa6wxHisgAMCkU | [Group 49 1st meeting] : 30 | V87MYN_Sy0qJgvKIHm2EVMgAEggU |  | Completed | Medium | a707c21a-ae80-4a96-9809-71b38104eefb;fbf7c6e5-5096-4832-be13-ae3a8b7e3f66;ff7648f0-ec7a-4459-a9b2-dda9413432c9;e94ba878-f30a-4cb6-8d83-0fa53451575c;e34c9a79-4046-4931-9ad4-841f69cc8471 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 2026-08-15 | 2026-08-06 | 2026-08-06 |  | false | 2026-08-15 | ff7648f0-ec7a-4459-a9b2-dda9413432c9 | 3/3 | Sub Task 2;Sub Task 3;Sub Task 1 | 1st meeting completed | Description (Added by pm) On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Update Document Master-Document-EXAMPLE.docx Completion comment Done: Documented required fields for the team page (team name, project name, per-member photo/name/role, about-us blurb) and confirmed login work is styling-only, no auth logic changes. Deliverable: Requirements document, committed to the team repo. Note for next role: UX — we have 5 team members, one doesn't have a headshot yet, so the design needs a placeholder-avatar treatment. Two members also have longer blurbs, so don't assume a one-line blurb. Git URL: https://github.com/team-byte-size/team-page/blob/main/docs/requirements.md
6a7tE15QBkWzIcnQaYdaUcgAG1q- | Management Notes | V87MYN_Sy0qJgvKIHm2EVMgAEggU |  | Not started | Medium |  | 9fd1a906-36d9-496e-93d9-7d669f31fb12 | 2026-08-15 |  |  |  | false | [5 empty] | Not much done and work started without moving things into doing

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
8O89xBuC7kaP7OHsHMUXfcgAEDtE | Blocked
V87MYN_Sy0qJgvKIHm2EVMgAEggU | Documents & Updates
5bW2CwKTIEa4GTtTmu6ibsgAHren | Backlog
wgfV8Xi2wEyrcm9DikRxA8gAFE3W | Doing
KVjGgGyBbEmha9PiBZTEPcgAEZyE | Testing (if required)
yCYyGIXYk0WDHssor2qq3MgAGz3B | Reviewing
IyEBllnWwUC7l9NEEtdTxcgACfbp | Done
_O5uFu_e-EOHUIN9rm8-G8gAPt6o | Clean up

## Users
User ID | User Name | Email
ff7648f0-ec7a-4459-a9b2-dda9413432c9 | Sherlene Andrew | s4003502@student.rmit.edu.au
e34c9a79-4046-4931-9ad4-841f69cc8471 | Devlyn Jay | S3844511@student.rmit.edu.au
e94ba878-f30a-4cb6-8d83-0fa53451575c | Jonas Inocencio | S3787701@student.rmit.edu.au
fbf7c6e5-5096-4832-be13-ae3a8b7e3f66 | Thomas Williams | s4005637@student.rmit.edu.au
a707c21a-ae80-4a96-9809-71b38104eefb | Wangfung Chu | S3942078@student.rmit.edu.au
9fd1a906-36d9-496e-93d9-7d669f31fb12 | Alessio Bonti | alessio.bonti@rmit.edu.au